Team Members:

- Satya Indukuri (indukusa@mail.uc.edu)

- Kush Bhandari (bhandakh@mail.uc.edu)
Advisor: Hrishikesh Bhide

- Milestones List

| Milestone | Description / Deliverable | Planned Completion Date |
| --- | --- | --- |
| M1 – Requirements Specification | Define system requirements, project workflow, and roles; create initial documentation. | Dec 15, 2025. |
| M2 – Preprocessing Pipeline | Develop DICOM loader, 3D volume conversion, normalization, and lung isolation. | Jan 10, 2026 |
| M3 – Core ML Models | Design and implement nodule detection and segmentation models (3D CNN, U-Net/nnU-Net). | Feb 7, 2026 |
| M4 – Malignancy Classifier | Implement malignancy scoring model and integrate with detection outputs. | Feb 28, 2026 |
| M5 – Interface Development | Develop interactive visualization interface for nodule segmentation and risk scores.. | Mar 14, 2026 |
| M6 – Pipeline Integration | Integrate preprocessing, ML models, and interface into a functional end-to-end system. | Mar 28, 2026 |
| M7 – Testing & Validation | Test system with sample CT datasets, validate accuracy and performance, refine ML models. | Apr 11, 2026 |
| M8 – Documentation & Final Submission | Complete user manuals, technical documentation, and final project report. | Apr 26, 2026 |

- Table 1. Timeline:

| Task # | Task | Start Date | End Date | Responsible Member(s) |
| --- | --- | --- | --- | --- |
| 1 | Specify system requirements and workflow | Dec 8, 2025 | Dec 15, 2025 | Satya |
| 2 | Design 3D CT preprocessing pipeline | Dec 16, 2025 | Jan 10, 2026 | Kush |
| 3 | Develop DICOM loader & 3D volume conversion | Dec 16, 2025 | Jan 5, 2026 | Satya |
| 4 | Research 3D nodule detection models | Dec 16, 2025 | Dec 31, 2025 | Kush |
| 5 | Implement 3D CNN-based nodule detection | Jan 2, 2026 | Jan 31, 2026 | Kush |
| 6 | Design interface for visualizing ML outputs | Jan 15, 2026 | Feb 7, 2026 | Satya |
| 7 | Develop segmentation module (3D U-Net/nnU-Net) | Jan 15, 2026 | Feb 14, 2026 | Kush |
| 8 | Integrate preprocessing, detection, segmentation modules | Feb 1, 2026 | Feb 28, 2026 | Satya |
| 9 | Implement malignancy classifier | Feb 10, 2026 | Feb 28, 2026 | Kush |
| 10 | Test detection, segmentation, scoring modules | Mar 1, 2026 | Mar 10, 2026 | Kush |
| 11 | Develop visual overlays & measurements | Feb 15, 2026 | Mar 14, 2026 | Satya |
| 12 | Document preprocessing, detection, segmentation modules | Mar 1, 2026 | Mar 14, 2026 | Satya |
| 13 | Validate ML outputs against annotated datasets | Mar 11, 2026 | Mar 21, 2026 | Kush |
| 14 | Develop API endpoints for interface | Mar 1, 2026 | Mar 14, 2026 | Satya |
| 15 | Refine preprocessing and detection modules | Mar 15, 2026 | Mar 28, 2026 | Kush |
| 16 | Implement cloud deployment of inference pipeline | Mar 15, 2026 | Mar 28, 2026 | Satya |
| 17 | Test end-to-end system performance | Mar 29, 2026 | Apr 10, 2026 | Satya |
| 18 | Document interface design & API usage | Apr 1, 2026 | Apr 11, 2026 | Satya |
| 19 | Optimize ML models for inference speed and accuracy | Mar 22, 2026 | Apr 11, 2026 | Kush |
| 20 | Validate final system outputs with real or simulated data | Apr 12, 2026 | Apr 20, 2026 | Kush |

- Table 2. Effort Matrix:

| Task # | Task | Kush | Satya | Satya Hours | Kush Hours |
| --- | --- | --- | --- | --- | --- |
| 1 | Specify system requirements | 75% | 25% | 6 | 2 |
| 2 | Design preprocessing pipeline | 20% | 80% | 5 | 20 |
| 3 | Develop DICOM loader & 3D conversion | 80% | 20% | 12 | 3 |
| 4 | Research detection models | 33% | 67% | 4 | 8 |
| 5 | Implement 3D CNN detection | 15% | 85% | 5 | 35 |
| 6 | Design interface for ML outputs | 78% | 22% | 18 | 5 |
| 7 | Develop segmentation module | 15% | 85% | 5 | 30 |
| 8 | Integrate modules | 60% | 40% | 15 | 10 |
| 9 | Implement malignancy classifier | 20% | 80% | 4 | 20 |
| 10 | Test detection & segmentation | 20% | 80% | 3 | 12 |
| 11 | Develop visual overlays & measurements | 75% | 25% | 12 | 4 |
| 12 | Document preprocessing & detection modules | 80% | 20% | 8 | 2 |
| 13 | Validate ML outputs | 33% | 67% | 4 | 8 |
| 14 | Develop API endpoints | 77% | 23% | 10 | 3 |
| 15 | Refine preprocessing & detection | 30% | 70% | 4 | 10 |
| 16 | Implement cloud deployment | 75% | 25% | 12 | 4 |
| 17 | Test end-to-end performance | 73% | 27% | 8 | 3 |
| 18 | Document interface & API usage | 70% | 30% | 7 | 3 |
| 19 | Optimize ML models | 30% | 70% | 5 | 12 |
| 20 | Validate final outputs | 33% | 67% | 4 | 8 |